## VA SOP vs VAEC
| VA SOP | [7 empty] | VAEC
| (FedRAMP) | [7 empty] | (Cognosante)
Cloud-Based VA Application ATO Process | Appendix A | [8 empty] | assigned
PHASE | VA SOP | TASK | DESCRIPTION | REQ'D | ARTIFACT | TARGET | ASSIGNED | DUE(DONE)
| Appendix A | RV Entry | RiskVision Entry of cloud-based VA application | Y |  | RV
| Appendix A | App Q&A | CSP / VA Applicaiton questionnaire | Y |  | RV | SyO / ISO
| Appendix A | CRSP | Customer Responsibilities Security Plan | Y |  | RV | SyO / ISO
On-premises VA Application ATO Process
PHASE | VA SOP | TASK | DESCRIPTION | REQ'D | ARTIFACT | TARGET | ASSIGNED | DUE(DONE)
Pre-Requisites | 3.1 | ISO designation | Information Security Officer Designation | Y | person |  |  |  | 5.1 | ?EMPO Information Assurance (IA) Security Analyst
| 3.2 | RV Entry | RiskVistion System Inventory Checklist | Y | doc | RV |  |  | 5.3
Registration | 4.1.1 | App Reg | Application Registration | Y | doc |  |  |  | 5.4
Security Docs | 4.2.1 | SSP | System Security Plan | Y | doc | RV |  |  | 6.1.1
| 4.2.2 | MASA | Minor Application Self Assessment | N | doc | RV
| 4.2.3 | SA | Signatory Authority | CRSP | doc |  |  |  | 6.1.8
| 4.2.4 | RA | Risk Assessment | CRSP | doc |  |  |  | 6.1.10
| 4.2.5 | CMP | Configuration Management Plan | CRSP | doc | RV |  |  | 6.1.7
| 4.2.6 | IRP | Incident Response Plan | CRSP | doc | RV |  |  | 6.1.2
| 4.2.7 | ISCP | Informaton Security Contingency Plan | CRSP | doc | RV |  |  | 6.1.4
| 4.2.8 | DRP | Disaster Recovery Plan | CRSP | doc | RV |  |  | 6.1.3
| 4.2.9 | PIA | Privacy Impact Assessment | CRSP | doc | RV |  |  | 5.6
| 4.2.10 | ISA / MOU | Interconnection Security Agreeement / Memorandum of Understanding | CRSP | doc | RV |  |  | 6.1.6
| 4.2.11 | SDR | Secure Design Review | CRSP | doc |  |  |  | 5.5
| 4.2.4 | RA | Risk Assessment | CRSP | doc |  |  |  | 6.1.10
Technical / Testing | 4.3.1 | Nessus scan | Nessus scan | Y | scan | RV (TVM) |  |  | 6.2.1
| 4.3.1.1 | DB scan | Database scan | Y | scan |  |  |  | 6.2.2 | if contains a database
| 4.3.2 | QCR (V&V) | Quaility Code Review (Verification & Validation) | Y | code |  |  |  | 6.2.3
| 4.3.3 | SCR | Secure Code Review | Y | code |  |  |  | 6.2.4 | use VA static code analysis tools (M not supported; manual review)
| 4.3.4 | PT / AA | Penetration Test / Application Assessment | Y | code
| 4.3.5 | SCCD | Security Configuration Compliance Data | Y |  |  |  |  | 6.2.6
| 4.3.6 | SCA | Security Control Assessment | Y | code
| 4.3.7 | CIE | Control Implementation Evidence | Y | doc |  |  |  | 6.1.9
| 4.3.8 | EDS | Enterprise Discovery Scan | Y
OTHER |  | POA&M | Plan of Action and Milestone Remediation |  | ?? |  |  |  | 6.3
|  | AOSB | Authorizing Official System Brief |  | doc? |  |  |  | 6.4
|  | VIPR ID | Veteran Integrated Process Request ID |  | doc |  |  |  | 5.2
|  | PT / WASA | Penetration Test / Web Application Security Assessment |  | code |  |  |  | 6.2.5

## Appendix B
Authorization Requirements
Requirement |  | Roles / Responsibilities | References
Technical/Testing Requirements
| Nessus Scan | If the system’s Nessus Scan data is currently displayed in TVM within RiskVision: | · Contact OIS at: vaoisisrmrmf@va.gov with any questions.
| · A credentialed vulnerability scan against all instances of the operating system and desktop configurations must be conducted to identify security flaws. | Browse to Information Central Analytics and Metrics Platform (ICAMP) and use the Remediation Effort Entry Form (REEF) to document your manual remediation effort. For each deficiency identified from the scan, the System Owner or delegate creates a response within REEF for mitigating the deficiencies and / or provides evidence that the deficiencies have been mitigated. Also, include the scheduled completion date and status of each deficiency within REEF. | · TVM guidance material located on the OIS portal at Training and Brown Bag Materials
| · Actual scan results must be provided for analysis. | Once all manual remediation has been documented within REEF, run this report https://spsites.cdw.va.gov/sites/FODW_PVT/Progress%20Reports/Progress_ReportbyRegion_Chart.rdl within ICAMP.
| · All Critical and High deficiencies should be mitigated with documented mitigation evidence provided, and Moderate and Low deficiencies should be mitigated or have a documented mitigation plan. | Export the report by going to the upper left side of the screen select the Actions Menu. Choose Export and select Excel. Save the file.
| · Within the uploaded mitigation strategy, each system should conduct an analysis on the results of the vulnerability scans to determine and document those findings that are false positives, not applicable to the system, or otherwise mitigated. Additionally, findings that must be remediated through or from the vendor should also be documented as part of this analysis and should be documented. | System Owner or delegate then uploads the report from step 3 above to the Documents tab within RiskVision. Mitigation information can also be provided in the Vulnerabilities tab within RiskVision.
| · Refer to the Threat & Vulnerability Manager (TVM) guidance material located on the OIS portal at Training and Brown Bag Materials for detailed information on how to access TVM within RiskVision. | Within the uploaded mitigation strategy, each system should conduct an analysis on the results of the vulnerability scans to determine and document those findings that are false positives, not applicable to the system, or otherwise mitigated. Additionally, findings that must be remediated through or from the vendor should also be documented as part of this analysis.
If the system’s Nessus Scan data is not currently displayed in TVM within RiskVision:
· : If Nessus Scan data is not currently provided in TVM for the system and instead raw Nessus Scan results exist from CSOC, the System Owner or delegate shall upload the actual Nessus Scan results to the Documents tab in RiskVision; along with a mitigation strategy for each finding. Also, within ICAMP, if the ISO/System Owner does not have an option to pull a report for their FISMA reportable system, then contact the VA GRC Service Desk to provide the IP address range of the system authorization boundary to add it to ICAMP to pull the report.
· System Owner or delegate creates one finding and a response in the Findings tab within RiskVision for the Nessus scan to serve as a reminder to resolve the deficiencies.
| Quality Code Review | V&V Quality Code Reviews | · For detailed instructions on the code reviews process, reference the VA Quality Code Review SOP and guidance materials, which are posted on the VA SwA Program Office Resource Site.
| · Quality code reviews of custom developed VA applications using the approved VA static code analysis tool should be conducted to identify code quality issues within VA applications. | · VA Application Developers open a NSD ticket [(855) NSD-HELP] to request VA static code analysis tools in order to perform scans according to the procedures in the VA Quality Code Review SOP and guidance materials.
| · Applications written in languages that are not supported, such as MUMPS, shall be targeted for manual review of testing with other applicable tools; notify the VA Software Assurance (SwA) Program Office if this is the case at: OISSwASupportGroup@va.gov. | · VA Application Developers scan their own application source code.
· VA Application Developers open a NSD ticket [(855) NSD-HELP] to request validation of a final V&V quality code review.
· VA Application Developers deliver the scan results to the VA SwA Program Office at: OISSwASupportGroup@va.gov for review, work with the VA SwA Program Office to schedule the validation, and coordinate with them to resolve any issues identified during validation.
· The scan results are reviewed to ensure that minimum VA standards have been met. The VA SwA Program Office determines whether additional analysis is needed, and works with the VA Application Developers to ensure that they understand how to meet the standards required.
· System Owner or delegate uploads full test results to the Documents tab in RiskVision.
· System Owner or delegate creates a response for mitigating the deficiencies and/or provides evidence that the deficiencies have been mitigated for each deficiency identified from the V&V quality code review. Also, include the scheduled completion date and status of each deficiency. Information should be provided in Excel or Word format; refer to the OIS preferred template located on the OIS Portal at A&A Home Documents. System Owner or delegate uploads the aforementioned document to the Documents tab in RiskVision.
· System Owner or delegate creates one finding and a response in the Findings tab within RiskVision for the V&V quality code review to serve as a reminder to resolve the deficiencies.
| Secure Code Review | V&V Secure Code Reviews | · Contact the NSD Help Desk [(855) NSD-HELP] to request tools (Fortify), reviews, or technical support
| · V&V secure code reviews of custom developed VA applications must be conducted according to the VA Secure Code Review SOP located at | · VA Application Developers open a NSD ticket [(855) NSD-HELP] to request VA static code analysis tools; they scan their own application source code; open a NSD ticket to request validation of a final V&V secure code review; deliver the scan results to the VA SwA Program Office at OISSwASupportGroup@va.gov for review; work with the VA SwA Program Office to schedule the validation; and coordinate with them to resolve any issues identified during validation.
· System Owner or delegate is responsible for coordinating the mitigation of deficiencies, documenting the mitigation plans, and uploading them along with the secure code review results to RiskVision under Entity Details: Documents tab.
| VA SwA Program Office Resource | · System Owner or delegate creates one finding and a response in the Findings tab within RiskVision for the secure code review to serve as a reminder to resolve the deficiencies.
· V&V secure code reviews are conducted by the VA Application Developers.
· Applications written in languages that are not supported, such as MUMPS, shall be targeted for manual review or testing with other applicable tools (notify OIS if this is the case at: OISSwASupportGroup@va.gov).
| Penetration Test/Application Assessment | · System Owner or delegate contacts ISRM at vaoisisrmrmf@va.gov to request penetration test/application assessment from CSOC. | · Contact OIS at: vaoisisrmrmf@va.gov with any questions
| · A full penetration test/application assessment must be performed that includes automated and manual assessment tools and techniques on Internet Facing and/or High Impact Systems. | · CSOC conducts penetration test/application assessment and provides results to system POCs. Please allow 30 days for CSOC to schedule/conduct the penetration test/application assessment.
| · For Internet facing applications, if the application utilizes multiple servers then a WASA and Penetration Test are required, regardless of the FIPS categorization. If the Internet facing application only uses one server then only a WASA is required. | · System Owner or delegate is responsible for coordinating the mitigation of deficiencies, documenting the mitigation plans, and uploading them along with the test results to RiskVision under Entity Details: Documents tab.
| · Actual test results must be provided for analysis. | · System Owner or delegate creates one finding and a response in the Findings tab within RiskVision for the penetration test/application assessment to serve as a reminder to resolve the deficiencies.
· All Critical and High deficiencies should be mitigated with documented mitigation evidence provided, and Moderate and Low deficiencies should be mitigated or have a documented mitigation plan.
| Security Control Assessment (SCA) (if applicable) | · Once notified by OIS that an SCA is required, the appropriate audit team will be notified by OCS to schedule the assessment. | · Contact OIS at: vaoisisrmrmf@va.gov
| · An SCA will be required only upon request from OIS. | · The assigned audit team will conduct the SCA.
| · If an SCA is required, all Critical and High POA&Ms should be mitigated with documented mitigation evidence provided, and Moderate and Low POA&Ms should be mitigated or have a documented mitigation plan. | · OIS will create a SCA program for the appropriate entity in GRC that was audited.
· The audit team lead will upload the deliverables, to include the SCA report and import the POAMs, within 4 weeks of completion of the audit.
· System Owner or delegate creates responses to the POAMs/findings within 15 days of the POAMs uploaded.
| Security Configuration Compliance Data | For systems with IP address ranges internal to the VA that have the IBM BigFix agent installed: | · Contact OIS at: vaoisisrmrmf@va.gov and CSOC, or the Enterprise Visibility Team at: OISEVSupportGroup@va.gov with any questions
| · Compliance data must be obtained for all IP addresses that make up a system and must check against VA approved hardening guidance for all Operating Systems, Databases, Networks, and Security Devices, where guidance exists. The Security Configuration Compliance Data requires a 90% compliance for a full ATO. | · System Owner/Delegate should verify their IP addresses or system names by reviewing the boundaries displayed in the Enterprise Visibility and Vulnerability Management (EVVM) Dashboard. Regional GSS boundaries can be found at: https://dashboard.tic.va.gov/s/290/ | · Internal Compliance reports location: https://dashboard.tic.va.gov > Enterprise > All Systems > Authorization & Accreditation
|  | · Facility GSS and System boundaries can be found at: https://dashboard.tic.va.gov/s/291/. If there are any discrepancies found please send an email to the ISRM (vaoisisrmrmf@va.gov) and CC the OIS EV Support Group (OISEVSupportGroup@va.gov). | · OIS preferred template location on the OIS Portal at A&A Home Documents
· After reviewing information system boundaries for accuracy, System Owner/Delegate should run the Security Configuration Compliance Data (SCCD) Checklist Trending and Compliance Trending reports and export them to PDF from the EVVM Dashboard (https://dashboard.tic.va.gov > Enterprise > All Systems > Authorization & Accreditation). Checklist Trending reports are located at:
Regional GSS: https://dashboard.tic.va.gov/s/28T/
Facility GSS: https://dashboard.tic.va.gov/s/28V/
System: https://dashboard.tic.va.gov/s/28X/
Compliance Trending reports are located at:
Regional GSS: https://dashboard.tic.va.gov/s/28U/
Facility GSS: https://dashboard.tic.va.gov/s/28W/
System: https://dashboard.tic.va.gov/s/28Y/
When running the compliance reports please select the applicable information system (Note: Both boundary data and compliance data are updated nightly).
For systems with IP address ranges external to the VA or for systems without the IBM BigFix agent installed yet: The IBM BigFix agent must be installed to receive SCCD. For systems that used to have CSOC provide SCCD, IBM BigFix is outside the scope of the CSOC vulnerability scanning team and CSOC no longer provides SCCD. The System Owner or delegate must ensure the following steps are completed in order to obtain SCCD from IBM BigFix.
· The system must be defined in RiskVision.
· The IP addresses/IP address range of all hosts (servers/workstations) that make up the system must be captured in RiskVision. The System Owner or delegate contacts ISRM at vaoisisrmrmf@va.gov to ensure the IP addresses or system names that make up their system(s) are appropriately tagged or accounted for in RiskVision.
· The hosts must have the IBM BigFix agent installed. If the system owner or delegate has issues installing the IBM BigFix agent, then a ticket can be opened with the OIS EV Support team (OISEVSupportGroup@va.gov) to get it installed and functioning properly. Details of the system (FISMA boundary name/hostnames/IP addresses/system admin contact information) need to be included with the ticket request.
· System Owner or Delegate uploads the Compliance Trending and Checklist Trending reports to the Documents tab in RiskVision. The Compliance Trending and Checklist Trending reports can be found at https://dashboard.tic.va.gov/s/28U/ and https://dashboard.tic.va.gov/s/28T/, respectively.
· System Owner or Delegate creates one finding/POA&M and a response in the Findings tab within RiskVision for the SCCD to serve as a reminder to resolve the deficiencies.
· System Owner or Delegate continues to remediate deficiencies identified from the Compliance Trending and Checklist Trending reports.
· System Owner or Delegate uploads new Compliance Trending and Checklist Trending reports to Documents tab within RiskVision as evidence to show the remediation progress
Requirement |  | Roles / Responsibilities | References
Security Documentation Requirements
| System Security Plan (SSP) | · System Steward completes the assessments in RiskVision and develops findings and responses in the Findings tab for controls not in place. | · NIST SP 800-18 and VA Handbook 6500.3
| · The SSP is developed within RiskVision. | · ISO validates information added by the System Steward in RiskVision. | · Additional guidance for completion of the SSP can be provided by OIS
| · All required diagrams and confirmation of the security authorization boundary to include all devices and supporting software architecture should be included. | · The ISO, System Owner or delegate/System Steward exports the SSP from RiskVision and uploads the document to the Documents tab in RiskVision.
· All controls must be addressed. A finding will need to be created in RiskVision for every control that is not in place.
| Minor Application Self-Assessment | · The ISO, Project team, and the SS, working in conjunction should prepare the Minor Application Security Control Summary and provide implementation detail for all applicable security controls and upload the Self-Assessment to GSS/MA Documents repository in RiskVision. | · Minor Application Self Assessment SOP
| · Minor Application Self-Assessment must be completed for all minor applications. |  | (Appendix D)
| Signatory Authority | · System Owner or delegate completes the Signatory Authority using the template provided at A&A Home Documents and uploads the Signatory Authority to RiskVision under Entity Details: Documents tab. | · NIST SP 800-18
| · The Signatory Authority must be signed and dated by the appropriate parties. |  | · Additional guidance for completion of the Signatory Authority can be provided by OIS
| Risk Assessment (RA) | · System Steward completes the assessments in RiskVision. | · NIST SP 800-30
| · The RA is developed within RiskVision. | · ISO validates information added by the System Steward in RiskVision. | · Additional guidance for completion of the RA can be provided by the Office of Risk Management and Incident Reporting (RMIR)/OIS
· The ISO, System Owner or delegate/System Steward exports the RA from RiskVision and uploads the document to the Documents tab in RiskVision.
| Configuration Management Plan (CMP) | · System Owner or delegate completes the CMP using the template provided at A&A Home Documents and uploads the CMP as evidence to RiskVision under Entity Details: Documents tab. | · NIST SP 800-70 and VA Handbook 6500
| · The CMP should include processes for managing configuration and change management. |  | · Additional guidance for completion of the CMP can be provided by OIS
· The CMP should include infrastructure devices and baseline configurations (e.g., switches, routers, firewalls).
· The CMP should include a configuration file for each operating system(s), database(s), application(s), and network device(s) to validate compliance with baseline configuration.
| Incident Response Plan (IRP) | · System Owner works with the assigned ISO to create the IRP. | · NIST SP 800-61
| · The IRP must be created using RA and SSP. | · System Owner or designee uploads the signed IRP into RiskVision once completed and tested. | · Useful tools and websites:
| · The IRP must meet the following standards: |  | · Agiliance RiskVision Enterprise Operations GRC Instance
| · Information Access and Privacy Program |  | · Agiliance RiskVision National Release GRC Instance
| · NIST Special Publication 800-61 - Computer Security Incident Handling Guide |  | · OIS Cyber Security Portal
· VA Handbook 6500.3, Certification and Authorization of Federal Information Systems
· Each site is responsible for developing local level procedures incorporating VA-CSOC areas of responsibility.
| Information Security Contingency Plan (ISCP) | · System Owner or delegate develops or revises the Information System Contingency Plan. | · Useful tools and websites:
| · The ISCP must be created using following inputs: | · System Owner or designee uploads the Information System Contingency Plan into RiskVision. | · Agiliance RiskVision Enterprise Operations GRC Instance
| · Preliminary Information System Contingency Plan |  | · Agiliance RiskVision National Release GRC Instance
| · Primary Site System Security Plan |  | · OIS Cyber Security Portal
· Backup Site System Security Plan
· The ISCP must meet the following standards:
· NIST Special Publication 800-34 Rev. 1 - Contingency Planning Guide for Federal Information Systems
· Office of Information Security, Authorization Requirements Guide Standard Operating Procedures
· VA Handbook 6500.8, Information System Contingency Planning
| Disaster Recovery Plan (DRP) | · System Owner or designee develops the DRP as the entry point for the creation of both the facility and data center plans. | · Useful tools and websites:
| · The DRP must be created using following inputs: | · System Owner or designee uploads the DRP into RiskVision once completed and tested. | · Agiliance RiskVision Enterprise Operations GRC Instance
| · Primary Site System Security Plan |  | · Agiliance RiskVision National Release GRC Instance
| · Backup Site System Security Plan |  | · OIS Cyber Security Portal
· The DRP must meet the following standards:
· Office of Information Security, Authorization Requirements Guide Standard Operating Procedures
| Privacy Impact Assessment (PIA) | · System Owner, Privacy Officer, and ISO work together to submit a PTA, which is reviewed by the Privacy Services Office. After review and determination by analysts, the PTA must be signed by the System Owner, Privacy Officer, ISO, and any other relevant stakeholders and re-submitted to the Privacy Services Office via PIASupport@va.gov. If a PIA is required as an outcome of the PTA analysis by the Privacy Services Office, a PIA must be completed and submitted to the Privacy Services Office and then comments by the analysts, if any, must be incorporated. | · Authority is found in E-Government Act of 2002, OMB Circular 03-22, VA Directive 6502, VA Directive 6508, and VA Handbook 6508.1
| · A complete PIA must have: | · Privacy Services verifies PIA and provides results. | · Additional guidance for completion of the PIA/PTA can be provided by the Privacy Services Office. Any questions may be sent to PIASupport@va.gov
| · A previously completed Privacy Threshold Analysis (PTA). | · System Owner or delegate re-submits the PIA as a PDF file with the signatures of the System Owner, Privacy Officer, ISO, and any other relevant stakeholders to PIASupport@va.gov.
| · Been completed in the most up-to-date and Privacy Services approved template for both the PTA and PIA. The PTA and PIA template can be found at A&A Home Documents | · System Owner or delegate uploads the PIA to RiskVision under Entity Details: Documents tab.
· Been completed in coordination with the VA Privacy Services Office.
· Been signed by the System Owner, Privacy Officer, and ISO.
· Been re-submitted whenever there are major changes to the system or within 3 years.
| Interconnection Security Agreement (ISA)/ Memorandum of Understanding (MOU) | · System Owner in coordination with the entities identified in NIST SP 800-47 will complete the ISA/MOU using the latest template provided at: OIS Portal or A&A Home Documents. | · NIST SP 800-47, VA Handbook 6500, and FSS Bulletin#269
| · An ISA/MOU must be provided for all external interconnections. | · ISO will upload all final draft MOU/ISA documents to the MOU/ISA Review Submissions SharePoint site for a review prior to requesting signatures. | · Additional guidance can be provided by the Health Information Security Division at vafsshisd@va.gov or the OIT ERM CRISP Team at Sharon.mcallister@va.gov
· VA review team will assess the documents against a checklist for quality and content.
· Reviewer and the ISO will work collaboratively to correct deficiencies found in the documentation.
· Reviewer will notify the ISO via email informing them that the document is ready for signatures.
· ISO will process the document for signature.
· ISO will upload the document to the Enterprise Document SharePoint upon receipt of the completed and signed MOU/ISA document,.
· The finalized document should also be added to the existing A&A artifacts in RiskVision.