## RTEP-raw
Base Period
CLIN | DESCRIPTION | QTY | UNIT | UNIT PRICE | TOTAL PRICE
1 | Project Management in accordance with PWS paragraph 5.1 | 12 | MO | Not Separately Priced (NSP) | NSP
This CLIN includes all labor, materials, and supplies required for the successful completion of the services detailed in PWS Paragraphs 5.1 and 6.0, and its subsections.
Period of Performance (PoP) is 12 months from date of award.
*Cost of Project Management tasks and deliverables shall be allocated to CLINs 0002-0005.
0001AA | Contractor Project Management Plan in accordance with PWS paragraph 5.1.1 | 12 | LO | NSP | NSP
Due 30 days after receipt of order (ARO) and updated monthly thereafter throughout the PoP.
0001AB | Monthly Progress Report in accordance with PWS paragraph 5.1.2 | 12 | LO | NSP | NSP
Due 30 days ARO and updated monthly thereafter throughout the PoP.
0001AC | VA Privacy and Information Security Awareness and Rules of Behavior Training Certificate in accordance with PWS paragraph 5.1.4 | 1 | LO | NSP | NSP
Due 5 days ARO or five (5) days after new resource onboarded.
0001AD | Signed Contractor Rules of Behavior in accordance with PWS paragraph 5.1.4 | 1 | LO | NSP | NSP
Due 5 days ARO or five (5) days after new resource onboarded.
0001AE | VA HIPAA Certificate of Completion in accordance with PWS paragraph 5.1.4 | 1 | LO | NSP | NSP
Due 5 days ARO or five (5) days after new resource onboarded.
0001AF | Onboarding Status Report in accordance with PWS paragraph 5.1.5 | 1 | LO | NSP | NSP
Due 5 days ARO and updated weekly thereafter until completed; then only as needed.
2 | Adaptive Maintenance Services in accordance with PWS Paragraph 5.2. | 12 | MO | $ | $
This CLIN includes all labor, materials, and supplies required for the successful completion of the services detailed in PWS Paragraphs 5.2.
PoP is 12 months from date of award.
0002AA | Comprehensive RPC Interface Audit Report in accordance with PWS Paragraph 5.2. | 4 | LO | NSP | NSP
Due 90 days ARO and updated quarterly thereafter.
0002AB | Massachusetts General Hospital Utility Multi-Programming System (MUMPS) remote procedure call RPC to JSON Model Data Definition in accordance with PWS Paragraph 5.2. | 4 | LO | NSP | NSP
Due 90 days ARO and updated quarterly thereafter
Electronic submission to: RTC code repository with notification to VA PM, COR and CS
0002AC | Version Description Document (VDD) in accordance with PWS Paragraph 5.2. | 4 | LO | NSP | NSP
Due 90 days ARO and updated quarterly thereafter
0002AD | Automated CloudWatch Configuration in accordance with PWS Paragraph 5.2. | 4 | LO | NSP | NSP
Due 90 days ARO and updated quarterly thereafter
0002AE | Security Vulnerability Report in accordance with PWS Paragraph 5.2. | 4 | LO | NSP | NSP
Due 90 days ARO and updated quarterly thereafter
3 | Testing in accordance with PWS Paragraph 5.3. | 12 | MO | $ | $
This CLIN includes all labor, materials, and supplies required for the successful completion of the services detailed in PWS Paragraphs 5.3.
PoP is 12 months from date of award.
0003AA | Master Test Plan | 11 | LO | NSP | NSP
Draft Due 30 days ARO
Final Due 60 days ARO and updated monthly thereafter
0003AB | RPC Interface Test Suite | 4 | LO | NSP | NSP
Due 90 days ARO and updated quarterly thereafter
4 | Assessment and Authorization Support in accordance with PWS Paragraph 5.4. | 12 | MO | $ | $
This CLIN includes all labor, materials, and supplies required for the successful completion of the services detailed in PWS Paragraph 5.4.
PoP is 12 months from date of award.
5 | Initial Operating Capability Support in accordance with PWS Paragraph 5.5. | 12 | MO | $ | $
This CLIN includes all labor, materials, and supplies required for the successful completion of the services detailed in PWS Paragraph 5.5.
PoP is 12 months from date of award.
0005AA | Production Operations Manual (POM) in accordance with PWS Paragraph 5.5. | 1 | LO | NSP | NSP
Due 90 days ARO and updated quarterly
0005AB | Deployment and Installation Guide in accordance with PWS Paragraph 5.5. | 1 | LO | NSP | NSP
Due 90 days ARO and updated quarterly
0005AC | User Manual in accordance with PWS Paragraph 5.5. | 1 | LO | NSP | NSP
Due 90 days ARO and updated quarterly
6 | Release and Deployment Support in accordance with PWS Paragraph 5.6. | 12 | MO | $ | $
This CLIN includes all labor, materials, and supplies required for the successful completion of the services detailed in PWS Paragraph 5.6.
PoP is 12 months from date of award.
0006AA | Capacity, Performance, and Scalability Assessment for National Deployment in accordance with PWS Paragraph 5.6. | 1 | LO | NSP | NSP
Draft: Due 30 days after IOC deployment
Final: Due 60 days after IOC deployment, updated monthly thereafter.
Base Period Total: |  |  |  |  | $

## RTEP-main
CLIN | PWS | Contractor | DESCRIPTION | QTY | DUE | Updated
1 | 5.1, 6.0 | AV | Project Management | 12 |  | monthly
1AA | 5.1.1 | AV | Contractor Project Management Plan (CPMP) | 12 |  | monthly
1AB | 5.1.2 | AV | Monthly Progress Report | 12 |  | monthly
1AC | 5.1.4 | AV | VA Privacy and Information Security Awareness and Rules of Behavior Training Certificate | 1 | 5d ARO
1AD | 5.1.4 | AV | Signed Contractor Rules of Behavior (ROB) | 1 | 5d ARO
1AE | 5.1.4 | AV | VA HIPAA Certificate of Completion | 1 | 5d ARO
1AF | 5.1.5 | AV | Onboarding Status Report | 1 | 5d ARO
2 | 5.2 | HRG/CG | Adaptive Maintenance Services | 12 mo | continous | continous
2AA | 5.2 | HRG/CG | Comprehensive RPC Interface Audit Report | 4 | 90d ARO | quarterly
2AB | 5.2 | HRG/CG | MUMPS RPC to JSON Model Data Definition | 4 | 90 ARO | quarterly
2AC | 5.2 | HRG/CG | Version Description Document (VDD) | 4 | 90 ARO | quarterly
2AD | 5.2.5 | HRG/CG | Automated CloudWatch Configuration | 4 | 90 ARO | quarterly
2AE | 5.2.8 | HRG/CG | Security Vulnerability Report | 4 | 90 ARO | quarterly
3 | 5.3 | HRG/CG | Testing | 12 mo | continous | continous
3AA |  | AV | Master Test Plan | 11 | 60d ARO | monthly
3AB |  | HRG/CG | RPC Interface Test Suite | 4 | 90d ARO | quarterly
4 | 5.4 | AV | Assessment and Authorization Support | 12 mo | continous | continous
5 | 5.5 | AV | Initial Operating Capability Support | 12 mo | continous | continous
5AA | 5.5 | AV | Production Operations Manual (POM) | 1 | 90d ARO | quarterly
5AB | 5.5 | AV | Deployment and Installation Guide | 1 | 90d ARO | quarterly
5AC | 5.5 | AV | User Manual | 1 | 90d ARO | quarterly
6 | 5.6 | AV | Release and Deployment Support | 12 mo
6AA | 5.6 | AV | Capacity, Performance, and Scalability Assessment for National Deployment | 1 | 30d after IOC

## AV-A&A
VAEC A&A Artifact | Our Approach
System Security Plan (SSP) [PWS Deliverable 5.4-1]: The SSP a formal document that provides an overview of the security requirements for the information system and includes the security controls that are in place or planned. The SSP is generated using a GRC tool such as RiskVision with plans to change to eMASS Summer 2019. | AbleVets system security engineer will request System Steward access to RiskVision in order to maintain and edit the SSP security requirements. We will add security Engineer will update annually or when there is a major change.RiskVision workflows to gain approval. The System SecuritySystem Security Officer (ISSO) to push the SSP through thecontrol evidence for those security controls that are planned and will update those security controls that are in place. We will work closely with the Information
Security Configuration Plan [PWS Deliverable 5.4-2], also known as the Configuration Management Plan (CMP): The CMP document defines the change management process and evaluates change for potential adverse impacts. | The CMP is a security artifact that supports identification, control and auditing of VAEC and VAM assets in an orderly and controlled manner. The system security engineer will implement the CMP using the VAEC AWS CMP template. Additionally, the system security engineer is responsible for ensuring that the change has been reviewed and analyzed for impact to security through the security impact analysis process. The CMP will be approved by both the VAEC and VAM stakeholders’ team. Once approved the system security engineer will upload to Risk Vision. The System Security Engineer will update annually or when there is a major change.
Information System Contingency Plan (ISCP) [PWS Deliverable 5.4-3]: This plan contains interim measures to recover information system services after a disruption. | AbleVets system security engineer will utilize the VAEC ISCP template as it has already established procedure to recover VAEC AWS or Azure objectives. We will complete the template by inserting VAM program information in appropriate sections. Once approved by VAEC and VAM stakeholders the plan will go through a review and test on an annually basis. Results of the test will be documented in an after-action report. The System Security Engineer will update annually or when there is a major change.
Incident Response Plan [PWS Deliverable 5.4-4]: An IRP is necessary for rapidly detecting incidents, minimizing loss and destruction, mitigating the weaknesses that were exploited, and restoring computing services. | Our system security engineer will work closely with the System Owner (SO) and ISSO in the creation and maintenance of the IRP. We will implement the IRP using the IRP template from OIS ATO SharePoint site. Once the IRP is approved it will be uploaded to the Risk Vison document tab. This is important to upload to as the Security Control Assessment testing will review for compliance. The System Security Engineer will update annually or when there is a major change.
Privacy Impact Assessment (PIA) [PWS Deliverable 5.4-5]: The PIA identifies and mitigates the major potential privacy and security risks associated with the use of Sensitive Personal Information (SPI), and ensure the use of privacy protections compatible with the identified risks. | The Privacy Impact Assessment is conducted by the Privacy Officer. AbleVets system security engineering will work alongside the Privacy Officer to ensure it is updated every three years. The security engineer will upload the updated PIA to Risk Vision when complete.
Risk Assessment [PWS Deliverable 5.4-6]: Provides the Risk Profile of the system after all security evidence has been provided. | The Risk Assessment is conducted in Risk Vision. The system security engineer will complete the questionnaire to generate the Risk Assessment report. The ISSO will validate. Upon approval the system security engineer will export the Risk Assessment from Risk Vision and upload to the artifacts tab in Risk Vision. The RA will be completed on an annual basis or when major changes in the data occur.
Security Configuration Checklist (SCC) [PWS Deliverable 5.4-7]: The SCC is part of the Security Compliance Configuration Data (SCCD) as required by the VAEC ATO Guide and Authorization Requirements SOP Guide. All accreditation boundaries that contain an operating system are required to provide Security Configuration Compliance Data. | AbleVets system security engineer will work closely with the SO and SSO to ensure the SCCD are tagged or accounted for in RiskVision and will run the Checklist Trending and Compliance Trending reports. These reports will be exported as PDF from the EVVM Dashboard and uploaded to RiskVision artifacts tab. SCCD will be pulled on a quarterly basis or when changes are made to the approved secure configuration/hardening guides or as requested by OIS.
System Interconnection Agreement (MOU and interconnection) [PWS Deliverable 5.4-8]: The system interconnection agreement document is also known as the Interconnection Security Agreement and Memorandum of Understanding (ISA/MOU) in the Authorization Requirements SOP Guide. ISA/MOU is required to authorize a connection between information systems that do not share the same Authorizing Official and is necessary for all external connections. | Our system security engineer will work closely with the ISSO and VAM technical team to ensure the MOU/ISA template is complete. It is necessary to involve the SO, PM and technical project members to ensure the connection ports, protocols and services are captured correctly. Once complete the ISSO or system security engineer will upload the MOU/ISA to the Review Submission SharePoint. Once the review team is satisfied, the ISSO will proceed with approval signatures, upload to the Enterprise Document SharePoint while the security engineer will upload to Risk Vision. This document will be reviewed on an annual basis or if there are significant changes.
Interconnection Security Agreement [PWS Deliverable 5.4-9]: | Same document as above.
Signatory Authority [PWS Deliverable 5.4-10]: Provides the approval of the System Security Plan and is signed by the System Owner and ISSO. | AbleVets system security engineer will assist with the Authorization package to ensure all documentation is complete and ready for the closely with the ISSO to ensure all forms are completed and signed.Authorizing Official. The System Security Engineer will work