## Sheet1
Number | Document | Comment from Bobbi | Status as of 05-28-2019 | Due Date
1 | CMP | Document should be finalized before routing for signatures. | Working on it | 5/31/2019 with few questions required help from Dev Team
1.1 |  | Remove all colored text/instructions. | Done
1.2 |  | The controls identified in the VAEC CRM will need to be addressed in the CMP. | Done
1.3 |  | Current templates provided indicate VAEC signatures are on file. This will remain the same. | No Change Required
1.4.1 |  | Information should be specific to VAM. Information looks to be copied from another system. | Done
1.4.2 |  | Organizational references outdated and references DCO which is AITC. | Done
1.4.3 |  | Duties identified in CMP are in conflict with separation of duties requirement. | Pending
1.4.4 |  | Get with COMS representative, | Done
1.4.5 |  | BCM site - https://vaww.vashare.oit.va.gov/sites/itops/svcs/sma/BCM/Pages/BCM.aspx, | Done
1.46 |  | KS site - https://vaww.vashare.oit.va.gov/sites/ois/knowledgeservice/pages/home.aspx and VA Handbook 6500 for additional information. | Done
1.4.7 |  | VA Handbook 6500 for additional information. | Done
1.5 |  | Recommend completing this document as the environment is put into place (at least preprod) to identify the appropriate contacts and procedures. | CMP will be uploaded to RiskVision after Signatures. It will be in RiskVision regardless of environment status. And it is considered a Live Document due to the fact that it will require changes all the way through the life of the project
1.6 |  | Double check ISSO duties identified in document. | Done
1.7 |  | Stopped halfway through document. Whole document needs to be reworked. | By the incorporating the above recommendation and adjusting the language overall, this is now complete.
2 | BIA | Expect all critical processes be identified. Document does not require ISSO signature. | Pending. Will require a 5-10 minutes fix. | 2019-05-30
3 | DRP | Recovery processes for the VAM system, and references, without viable links | Done | 2019-05-31
3.1 |  | Remove all colored text/instructions. | Done
3.2 |  | PO does not typically sign these documents | OK. Removed Signature Block for PO. Just FYI it is part of the new template. However, made the change as per ISO guidance
3.3 |  | The ISCP and DRP should support each. Data is different in both docs. | 90% Done. David and Piyush will do a side-by-side review to complete.
3.4 |  | Appendix A - DRP Personnel Contact Data - VA DRP specific key personnel and contact information - VAM | Updated. Added Rahul as Dev-Ops Engineer
3.5 |  | Appendix B - Call Tree Recovery personnel, and facility POCs should be alerted - VAM | Updated. Added Rahul as Dev-Ops Engineer
3.6 |  | Appendix D – Alternate Storage Site Complete this. | Complete
3.7 |  | Appendix F - Recovery Site Recovery and reconstitution procedures - VAM | Done
3.8 |  | Appendix G - Associated Plans High-level activities that occur during the recovery of VAEC AWS’s and VistA Adaptive Maintenance (VAM) system, data and operations are identified (see comments in DRP. Make sure Appendix matches DRP. Complete Version. | Pending completion when all ATO documents are finalized.
4 | ISCP | In the event the ISCP is activated, it will need procedures documented for Activation and notification, Recovery, and Reconstitution. | If VAM application is not functioning properly for whatever reason, compromised, or inoperable -- what is the contingency plan? This is a question for either Dr. Richards and/or Conor. Aside insider threats, project members can only mitigate potential issues (limited) through phone call or email to VA or AWS specific contacts. The vast majority of all issues relative to recover and reconstitution is the reponsibility of VA Enterprise, VAEC, and CSP. | 2019-05-31
4.1 |  | Remove all colored text/instructions. | Done
4.2 |  | ISCP threat values are copied from VAEC AWS identified threats. If they are indeed the same, still need to evaluate the risk specific to VAM. Added a threat value spreadsheet that will help you align the threats to the controls. Use this w/CRM for appropriate threat identification for VAM. | Checked for inherited threats for its pertinence. See comment in Question 4 above for VAM Specific threats.
4.3 |  | PO does not typically sign these documents | OK. Removed Signature Block for PO. Just FYI it is part of the new template. However, made the change as per ISO guidance
4.4 |  | Appendix A – Personnel Contact Data - VA Complete tables specific to VAM. | Pending
4.5 |  | Appendix E - Alternate Storage Facility for alternate storage site details – need to complete table. | Complete. This is Inherited through VAEC and CSP
4.6 |  | Appendix F – Alternate Processing Procedures Complete this. | As far as our current knowledge if VAM is down, VAEC is down. Need to understand from Conor if there is a back up or work around this issue.
4.7 |  | Appendix I – Data Backup Complete this. | Complete. Inherited thorugh CSP and VAEC
4.8 |  | Appendix J – Detailed Recovery Procedures Complete this. | Refer to Question 4 above.
4.9 |  | Appendix K - Data and Functionality Validation Testing Procedures For the data validation and functionality testing procedures – Complete this. | This partially inherited through the VA Enterprise and pending pre-prod data and functionality testing.
4.10 |  | Appendix L – Concurrent Processing Complete this. | Does not Apply to VAM. Need Confirmation from Tom and Conor.
4.11 |  | Appendix M - Cleanup for the cleanup procedures – Complete this. | Largely Inherited through CSP and VAEC.
5 | PIA |  |  | Update complete on 5/28/2019
5.1 |  | PIA has to match the PTA. If it does not, both will need to be redone. PTA dated 8/28/2018. | PTA was signedon 4-24-2019. PTA reference has been updated.
5.2 |  | PTA and PIA have to be routed and approved by PIA Support Group before being routed for signatures. | PTA is approved and PIA will be sent thorugh PIA Support Group before being routed for Signatures.
5.3 |  | AWS services identified need to be approved before they are authorized for use. | Kinesis Streams and AWS Logs are approved.
6 | SSC | Recommend the Business Representative Sign this document as well. | We will add Dr. Richard's Signature Block to this document | 2019-05-29
|  | ISSO signature provided. See attached | Thank you.
7 | SIA |  |  | 5/31/2019 with few questions required help from Dev Team
7.1 |  | Need to update the Security Family Questionnaire. The system does not inherit all controls from VAEC AWS. The team is responsible for documenting the controls from the Customer Responsibility Matrix. This has been provided. | Done
7.2 |  | The only connection identified are R1-4 VistA (CPRS) | Pending. Get Verification on Connections from Conor
8 | Privacy Controls |  |  | Update complete on 5/28/2019
8.1 |  | (from the VAEC CRM dtd 3/8/19) - The VAEC itself has no PII/PHI. Every application must complete a PTA and if required complete a PIA and address all privacy controls. | Done
8.2 |  | Also, see attached spreadsheet for documentation of required Privacy Controls. This will be uploaded to the Documents section w/RV. | Done